## Dashboard
Office Automation Suite — Master Build Tracker
42-day (6-week) build plan: Manager App + 10 automation modules
Start Date | 2026-07-09 |  | Overall % Complete | 0%
Target Launch Date | 2026-08-19
Days Elapsed | 0
Days Remaining | 42
Module Status Summary
Week | Focus Area | Modules | Status | % Complete
Week 1 (Day 1-7) | Foundation & walking skeleton | Invoice Parser (migrate), Meeting Summary (migrate), Manager App v0 | Not Started | 0%
Week 2 (Day 8-14) | Scheduling | Appointment Scheduling, Appointment Prep Research | Not Started | 0%
Week 3 (Day 15-21) | Email backbone | Email Management (triage + send, built as a reusable service) | Not Started | 0%
Week 4 (Day 22-28) | Revenue funnel, part 1 | Leads DB schema, Lead Generation, Prospecting | Not Started | 0%
Week 5 (Day 29-35) | Revenue funnel, part 2 + support | Follow-up, Customer Support | Not Started | 0%
Week 6 (Day 36-42) | Final app + orchestration + hardening | Content Creation, Manager App (full build), QA, deploy hardening | Not Started | 0%

## Daily Tracker
% Complete (all tasks): |  |  |  | 0% | Total tasks: | 42
Day | Week | Date | Task / App | Status | 0% | Notes
1 | Week 1 | 2026-07-09 | Repo scaffold, DB, deploy pipeline (Railway/Render) — get a live URL | Not Started
2 | Week 1 | 2026-07-10 | FastAPI skeleton + shared auth/db/email/calendar client modules | Not Started
3 | Week 1 | 2026-07-11 | Wrap invoice parser (TypeScript/Node) as its own HTTP service (/health, /run) | Not Started
4 | Week 1 | 2026-07-12 | Migrate Meeting Summary app into new backend | Not Started
5 | Week 1 | 2026-07-13 | Manager App v0: dashboard shell, module status view | Not Started
6 | Week 1 | 2026-07-14 | Manager App v0: manual trigger buttons for 2 migrated apps | Not Started
7 | Week 1 | 2026-07-15 | Week 1 review + fix issues (buffer) | Not Started
8 | Week 2 | 2026-07-16 | Appointment Scheduling: n8n prototype (calendar API auth + logic) | Not Started
9 | Week 2 | 2026-07-17 | Appointment Scheduling: port to Python module | Not Started
10 | Week 2 | 2026-07-18 | Appointment Scheduling: test + wire into Manager App | Not Started
11 | Week 2 | 2026-07-19 | Appointment Prep Research: n8n prototype (attendee/company lookups) | Not Started
12 | Week 2 | 2026-07-20 | Appointment Prep Research: port to Python module | Not Started
13 | Week 2 | 2026-07-21 | Appointment Prep Research: integrate with scheduling data + test | Not Started
14 | Week 2 | 2026-07-22 | Week 2 review + integration testing (buffer) | Not Started
15 | Week 3 | 2026-07-23 | Email Management: connect + authenticate all email accounts | Not Started
16 | Week 3 | 2026-07-24 | Email Management: categorization/triage logic prototype (n8n) | Not Started
17 | Week 3 | 2026-07-25 | Email Management: port core triage logic to Python | Not Started
18 | Week 3 | 2026-07-26 | Email Management: build as reusable service (callable by other apps) | Not Started
19 | Week 3 | 2026-07-27 | Email Management: build reusable send capability | Not Started
20 | Week 3 | 2026-07-28 | Email Management: test across all connected accounts | Not Started
21 | Week 3 | 2026-07-29 | Week 3 review + integration testing (buffer) | Not Started
22 | Week 4 | 2026-07-30 | Leads/contacts shared DB schema design | Not Started
23 | Week 4 | 2026-07-31 | Lead Generation: source integration + prototype (n8n) | Not Started
24 | Week 4 | 2026-08-01 | Lead Generation: port to Python, write to shared DB | Not Started
25 | Week 4 | 2026-08-02 | Lead Generation: test + validate data quality | Not Started
26 | Week 4 | 2026-08-03 | Prospecting: outreach logic prototype (n8n) | Not Started
27 | Week 4 | 2026-08-04 | Prospecting: port to Python, connect to leads DB | Not Started
28 | Week 4 | 2026-08-05 | Week 4 review + integration testing (buffer) | Not Started
29 | Week 5 | 2026-08-06 | Follow-up: sequencing/reminder logic prototype | Not Started
30 | Week 5 | 2026-08-07 | Follow-up: port to Python + integrate with leads funnel | Not Started
31 | Week 5 | 2026-08-08 | Follow-up: reuse Email Mgmt send service, test end-to-end | Not Started
32 | Week 5 | 2026-08-09 | Customer Support: ticket/inbox triage prototype | Not Started
33 | Week 5 | 2026-08-10 | Customer Support: port to Python, reuse Email Mgmt service | Not Started
34 | Week 5 | 2026-08-11 | Customer Support: test + validate | Not Started
35 | Week 5 | 2026-08-12 | Week 5 review + integration testing (buffer) | Not Started
36 | Week 6 | 2026-08-13 | Content Creation: prototype (drafts, templates) | Not Started
37 | Week 6 | 2026-08-14 | Content Creation: port to Python module | Not Started
38 | Week 6 | 2026-08-15 | Manager App: cross-module scheduling UI | Not Started
39 | Week 6 | 2026-08-16 | Manager App: unified logging + error alerts | Not Started
40 | Week 6 | 2026-08-17 | Manager App: polish + access controls | Not Started
41 | Week 6 | 2026-08-18 | End-to-end QA across all 10 modules | Not Started
42 | Week 6 | 2026-08-19 | Deploy hardening, backups, launch | Not Started

## App Backlog
# | App | Priority | Depends On | Build Method | Status | Notes
1 | Invoice Parser | Existing | — | Keep as Node/TS microservice; expose HTTP API for Manager App | Not Started | No rewrite — runs as its own service, called over HTTP
2 | Meeting Summary (Daily Digest) | Existing | — | Migrate existing script into FastAPI | Not Started | Already working; port logic, don't rebuild
3 | Appointment Scheduling | High | — | n8n prototype -> Python | Not Started | Core dependency for Prep Research
4 | Appointment Prep Research | High | Appointment Scheduling | n8n prototype -> Python | Not Started | Pulls meeting data to research attendees/companies
5 | Email Management | High | — | n8n prototype -> Python | Not Started | Build robust — Follow-up, Support, Prospecting depend on it
6 | Lead Generation | Medium | Email Management | n8n prototype -> Python | Not Started | Feeds shared leads/contacts DB
7 | Prospecting | Medium | Lead Generation | n8n prototype -> Python | Not Started | Reads from leads DB
8 | Follow-up | Medium | Prospecting, Email Mgmt | n8n prototype -> Python | Not Started | Reuses email sending + leads DB
9 | Customer Support | Medium | Email Management | n8n prototype -> Python | Not Started | Reuses inbox triage logic
10 | Content Creation | Low | — | n8n prototype -> Python | Not Started | Standalone, least urgent, build when time allows
11 | Manager App (Orchestrator) | Critical | All modules (incremental) | Python (FastAPI + dashboard) | Not Started | v0 in Week 1, full build Week 4

## Risk Log
Risk | Likelihood | Impact | Mitigation | Status
Building each app twice (no-code + Python) doubles timeline | Medium | High | Use n8n only to validate unfamiliar API logic; skip it for apps whose logic you already know | Open
Manager App scope creep before modules exist | Medium | High | Build Manager v0 as a thin shell in Week 1; add real orchestration only in Week 6 | Open
Email/Calendar API rate limits or auth issues | Medium | Medium | Test auth + rate limits in Week 1 before building app logic on top | Open
Shared leads DB schema changes mid-build breaks 3 apps | Medium | High | Finalize leads/contacts schema before starting Lead Gen (Day 22) | Open
Slippage compounds across 6 weeks without checkpoints | Low | Medium | Each week ends with a dedicated review/buffer day (7,14,21,28,35,41-42) to absorb slippage before it carries forward | Open
Running two runtimes (Python + Node) complicates deployment | Low | Low | Deploy as two services in the same Railway/Render project; Manager App treats the Node service like any other module via HTTP | Open